## Slide 1
Plan of action
The duration of the action will be 30 months (this includes 5 months for winding up the action and 1 month extra in case of delay).
Year 1 | Semester 1 |  |  |  |  |  | Semester 2 |  |  |  |  |  | 
Activity | Aug 2007 | Sep | Oct | Nov | Dec | Jan 2008 | Feb | Mar | Apr | May | Jun | Jul | Implementing body
0.1) Finalise all formalities with EC |  |  |  |  |  |  |  |  |  |  |  |  | Completed
0.2) Establishment separate project-office |  |  |  |  |  |  |  |  |  |  |  |  | Completed
3.2.1) Business meeting in Europe between Nepalese partners and EU partners for international kick-off , further introduction and more detailed planning of project:. |  |  |  |  |  |  |  |  |  |  |  |  | Completed
3.2.2) Determine and sign Memoranda of Understanding (MoU’s) for cooperation between European partners and -Nepal. |  |  |  |  |  |  |  |  |  |  |  |  | Completed
3.1.1) Organise a meeting for Nepalese IBOs. |  |  |  |  |  |  |  |  |  |  |  |  | Completed
3.1.2) Sign cooperation agreements between -Nepal and relevant Nepalese SME business IBOs in the network |  |  |  |  |  |  |  |  |  |  |  |  | Completed
2.1.1) Assessment of opportunities in -three- sub-sectors for potential trade between SMEs in the EU counterpart countries and Nepal. |  |  |  |  |  |  |  |  |  |  |  |  | Completed
1.1.1) Seminar on "Doing Business with the EU and particularly Great Britain" for IBOs in Nepal. |  |  |  |  |  |  |  |  |  |  |  |  | Completed
4.1) Administrative monitoring |  |  |  |  |  |  |  |  |  |  |  |  | Completed
4.2) Meetings Advisory Committee |  |  |  |  |  |  |  |  |  |  |  |  | Completed
4.3) Independent mid-term monitoring of process and results. |  |  |  |  |  |  |  |  |  |  |  |  | Completed
4.5) Administration |  |  |  |  |  |  |  |  |  |  |  |  | Completed

## Slide 2
Year 2 | Semester 3 |  |  |  |  |  | Semester 4 |  |  |  |  |  | 
Activity | Aug | Sep | Oct | Nov | Dec | Jan 2009 | Feb | Mar | Apr | May | Jun | Jul | Implementing body
1.1.6) 4 marketing / international business courses for Nepalese business IBOs. |  |  |  |  |  |  |  |  |  |  |  |  | Completed
2.1.2) General assessment of trade related procedures and requirements with specific reference to trade between Nepal and the EU partner |  |  |  |  |  |  |  |  |  |  |  |  | Ongoing
2.2.1) Determination of the system to exchange business information between Nepali IBOs and European partners. |  |  |  |  |  |  |  |  |  |  |  |  | Ongoing Lead Partner: DFSME
1.1.3) Seminar on ‘How to arrange and carry out Match-Making activities and events’ and ‘How to prepare and participate in Trade Fairs and Exhibitions’. |  |  |  |  |  |  |  |  |  |  |  |  | Completed
1.1.2) Seminar on ‘Chamber management and Administration’ and ‘Membership Recruitment’ for IBOs in Nepal. |  |  |  |  |  |  |  |  |  |  |  |  | Completed
1.1.5) Training on relevant EU/WTO quality and social standards issues applicable. |  |  |  |  |  |  |  |  |  |  |  |  | Completed
1.1.4) Seminar on International Documents and Payments’ and ‘Regional policy in Economy and Infrastructure -Lobbying and Advocacy-. |  |  |  |  |  |  |  |  |  |  |  |  | Completed
1.1.7) Training of Trainers course to Nepalese business IBOs on trade promotion services aimed at the EU market. |  |  |  |  |  |  |  |  |  |  |  |  | Completed
2.2.3) Preparation of first annual EU Trade Report by -Nepal -with support of European and Nepalese IBOs- for Nepalese IBOs and their members. |  |  |  |  |  |  |  |  |  |  |  |  | Ongoing
4.1) Administrative monitoring |  |  |  |  |  |  |  |  |  |  |  |  | Completed
4.2) Meetings Advisory Committee |  |  |  |  |  |  |  |  |  |  |  |  | Completed
4.5) Administration |  |  |  |  |  |  |  |  |  |  |  |  | Completed
4.6) Reporting |  |  |  |  |  |  |  |  |  |  |  |  | Completed

## Slide 3
Year 3 (wind-up of project) | Semester 5 |  |  |  |  |  | 
Activity | Aug | Sep | Oct | Nov | Dec | Jan 2010 | Implementing body
2.2.2) Direct mailing campaign to raise awareness among Nepalese SMEs of business opportunities in Europe and available knowledge among Nepalese IBOs. |  |  |  |  |  |  | Ongoing
3.2.3) Business meeting in for closure of the project, agree on future cooperation and evaluate the process and the results of the project. |  |  |  |  |  |  | Schedule on 31 August /01 September 2009 in Copenhagen, Denmark
4.1) Administrative monitoring |  |  |  |  |  |  | Will take place on completion of all project activities by Independent Expert on EC grants
4.2) Meetings Advisory Committee |  |  |  |  |  |  | 4 Advisory Committee meeting s to be completed
4.4 Independent evaluation of process and results. |  |  |  |  |  |  | Will take place on completion of all activities by Nepalese Consultant
4.5) Administration |  |  |  |  |  |  | -Nepal
4.6) Reporting |  |  |  |  |  |  | -Nepal
4.7) Audit |  |  |  |  |  |  | Chartered accountant